## Scope vs Built
Section | Scope item | Status | What is live / notes
A. Site configuration | Configure Shopify environment | Built | Store configured, single site, single language (English), single currency (USD).
A. Site configuration | Theme deployment workflow / Git | Built | Makro Core base theme, GitHub-synced live theme wt-farley/main, draft-first deploy process in active use.
A. Site configuration | Shopify native discount setup | Built | Native discount engine in place. No custom promotions scoped or built.
A. Site configuration | Shipping rates | Built | Order-value rate table plus a freight-quote profile configured via API on 11 Jul.
A. Site configuration | Branding API (checkout styling) | Verify | Confirm checkout logo, fonts and accent match the style guide before launch. Two-minute check in admin.
B. Core build | Style guide / pattern library | Built | Makro Core pattern library styled to the approved WT Farley design system (Figma).
B. Core build | Product card | Built | Global card used on PLP, search, sliders. Image delivery optimized 22 Jul (responsive sizes hints).
B. Core build | Product badges | Verify | Metafield-driven badge logic is in the theme. Confirm badge content is populated on real products.
B. Core build | Header navigation | Built + | Sticky header and menu (15 Jul). Extras beyond scope: SKU Lookup mode in the header search.
B. Core build | Mega menu | Built | Full mega menu rebuilt from the old site structure via API (11 Jul).
B. Core build | Footer navigation | Built | Social and legal links live. The three placeholder links flagged on 13 Jul (COA Finder, Catalog, Locations) no longer render.
B. Core build | Search dropdown | Built + | Quick-search redesigned into Categories + Products panels, plus the Lookup toggle. Part-number-shaped queries auto-route to Lookup as of 22 Jul; test SKUs removed from the markup.
B. Core build | Home page / global section library | Built | Homepage assembled from the section library, including the 18-card Shop by Category grid (Figma assets).
B. Core build | Search results / no results | Built | Search page has full collection-page parity: same grid, filters, toolbar.
B. Core build | PLP: grid, banner, filter, sort | Built | Collection banner, sticky filters and toolbar (15 Jul).
B. Core build | PLP: pagination | Partial | Delivered as infinite scroll instead of numbered pagination. Approved UX direction.
B. Core build | Category landing page | Built | Category grid template live (category cards link to collections).
B. Core build | PDP: product form and swatches | Built + | Custom pill dropdown with floating option list replaces the native variant select (Figma design).
B. Core build | PDP: media gallery | Built | Standard gallery on normal products. Configurator products get the dedicated preview panel (section C).
B. Core build | PDP: sections | Built | Documents accordion, specifications, product notes, certification images.
B. Core build | PDP: reviews and rating | Partial | Judge.me detected on the storefront. Scope named Yotpo. Confirm the app decision with the client and whether review widgets should show on PDP.
B. Core build | Custom contact us page | Built | /pages/contact live with the flexible form.
B. Core build | Mini cart | Built | Slide-out cart with line items, quantity, subtotal, checkout.
B. Core build | Cart page | Verify | Scope says /cart redirects home and opens the mini cart. /cart answers 200; confirm the behavior matches the scope assumption.
B. Core build | Auth flow pages | Built | Login, register, activate, reset, addresses templates styled in the theme.
B. Core build | Account pages | Verify | Scope assumes new Customer Accounts with passwordless login. Confirm which account experience is switched on.
B. Core build | Text content page templates | Built | About Us, FAQ, Terms, Testimonials, Dealer templates all live (8 pages in the sitemap).
B. Core build | 404 page styling | Built | Styled 404 template in theme.
B. Core build | Transactional emails | Verify | Confirm logo and accent color applied in Shopify email settings.
C. Custom features | Configurable Product Builder | Built + | 31 configurator products live (40 built, 8 held unpublished pending client content). Metaobject engine with price add-ons, live part number assembly, add to cart with selection properties, required-option blocking. Beyond scope: gas-type switcher without reload, layered hose preview on all 9 gas hoses, preview placeholder until first selection, Color Coding image swap, per-family headings.
C. Custom features | Part-Number Lookup | Built | Three entries: header Lookup mode, on-PDP lookup bar, ?sku= deep links. Middleware API resolves and routes to the right product with options prefilled, including partial part numbers. Known gap: legacy composite part numbers resolve to suggestions rather than exact matches (not variant SKUs by design).
C. Custom features | About Us CMS page | Built | /pages/about-us live.
C. Custom features | FAQ page | Built | /pages/faq live (template page.faq.json).
C. Custom features | Information slide-outs | Verify | Scope line is thin. Confirm whether the PDP documents accordion and product notes cover it or a slide-out is still expected.
D. Integrations | Shopify Search & Discovery | Built | Filters and facets running on PLP and search.
D. Integrations | Reviews and rating app | Partial | Judge.me scripts present on the storefront; scope assumed Yotpo. Align with client, then confirm placement.
D. Integrations | Cookie banner (Pandectes) | Built | Pandectes detected on the storefront.
D. Integrations | GA4 / GTM analytics | Built | GA4 runs through Shopify's Google & YouTube channel (confirmed 22 Jul), which is why no gtag/GTM snippet appears in storefront HTML. Klaviyo also present.
E. Platform and launch | Payment provider | Verify | Confirm Shopify Payments (or chosen gateway) is in live mode for launch.
E. Platform and launch | Tax management | Verify | Confirm tax settings against WT Farley's requirements.
E. Platform and launch | Domain setup | Open | Store still on wt-farley.myshopify.com. Domain cutover is a launch-day task.
E. Platform and launch | Sitemap and robots.txt | Built | Native sitemaps live and correct. The leftover page-template page was unpublished on 22 Jul.
E. Platform and launch | SEO: meta tags, friendly URLs | Built | Native handling. 9 product handles still end in -html (legacy import artifact); keep or rename with redirects.
E. Platform and launch | SEO: 301 redirects | Built | Legacy slug redirects live, plus the old _p_/_c_ .html pattern: 834 redirects imported 22 Jul (809 products, 25 categories, verified live, case-insensitive). 1,731 redirects total. 76 legacy URLs have no live equivalent.
E. Platform and launch | Content guides / training | Built + | 17-page Store Owner's Guide live on GitHub Pages (makro-agency.github.io/wt-farley-docs). Training session not yet scheduled.
E. Platform and launch | Pre-launch checklist / launch plan | Open | To be drafted once QA sign-off lands.
F. Data migration | Phase 1: Products | Built | 827 products migrated from Shift4Shop (760 active). Body cleanup 21 Jul: legacy shipping notice with a wrong phone number and Word markup removed from 34 products. 24 products now need descriptions; 2 active products have no image.
F. Data migration | Phase 2: Collections | Built | 92 smart collections (tag rules), none empty.
F. Data migration | Phase 3: Customers | Built | 11,274 customers imported.
F. Data migration | Phase 4: Orders | Built | 17,054 historical orders imported, email-matched to customers, archived/paid/fulfilled.
F. Data migration | Data decisions with client | Open | 30 SKUs shared across multiple products (cross-listings, one near-duplicate pair, OR-870A on two products at different prices). Client call needed on dedupe vs keep.

## QA Summary
Measure | Result
Report date | 22 July 2026
Store | wt-farley.myshopify.com
QA window | 10 to 22 July 2026
Configurator products passing every automated check | 31 / 31
Option choices validated against legacy data (price add-ons exact to the cent) | 1,500+
Historical orders migrated and verified by count | 17,054
Customers migrated | 11,274
Collections (none empty) | 92
Issues found by QA and fixed during the window | 15
Key pages loading clean, no template errors | 10 / 10
Redirects live in store (incl. 834 legacy .html imported 22 Jul) | 1,731
Method | Automated storefront + engine crawls, legacy-data comparison, admin data audit, manual Chrome passes, breakpoint checks (990px / 600px). Client validation matrix on the Validation Matrix tab.

## Found and Fixed
# | Issue | Found | Status | Verification
1 | Air Hose configurator missing its three core option groups (hose length, inlet, outlet were in draft status), so a valid part number could not be built. | 12 Jul | Fixed | All 6 groups live with full choice lists.
2 | 15-Foot Coiled Air Hose: a required option had zero visible choices (all four flagged hidden), which could block ordering. | 12 Jul | Fixed | Group renders with its choices.
3 | MRI Conditional Vacuum Hose showed the outlet picker twice, risking an ambiguous part number. | 12 Jul | Fixed | Single outlet group, positions unique.
4 | Legacy site URLs had no redirects: old links and search results would have landed on 404s after launch. | 10 Jul | Fixed | Slug redirects 301; .html pattern covered by the 22 Jul import (see #13).
5 | Two internal test products were live on the storefront at a $999,999 placeholder price. | 12 Jul | Fixed | Both return 404 on the storefront.
6 | 34 migrated product descriptions carried a legacy shipping notice with an out-of-date phone number, plus leftover Word markup. | 21 Jul | Fixed | Notice and markup removed across all 827 product descriptions.
7 | Configurator pages showed the product photo and pre-selected options on load, before the shopper chose anything. | 22 Jul | Fixed | Placeholder until first pick, nothing pre-selected, part number and price start blank. Layered hose products keep their existing behavior.
8 | Gas-type tiles misaligned on manifold products: banner artwork cropped, tiles at different heights. | 22 Jul | Fixed | Tiles top-aligned; wide artwork uncropped; hose tiles unchanged.
9 | Preview placeholder text read awkwardly on some products (Select a Choose Length), caught by the same-day automated re-check. | 22 Jul | Fixed | Copy reads correctly on all 22 placeholder products.
10 | Product card images downloaded far larger than displayed on desktop (full-screen renditions in card-size slots). | 22 Jul | Fixed | Browsers now pick card-size renditions: 50 to 70% less image transfer per card (sample: 52KB to 24KB or less).
11 | Placeholder links in the footer (COA Finder, Catalog, Locations) went nowhere. | 10 Jul | Fixed | No dead placeholder links render in the footer.
12 | Part numbers typed into the regular search returned nothing (composite part numbers are not stock SKUs). | 10 Jul | Fixed | Part-number-shaped queries now switch the header search to Lookup automatically; normal words stay in regular search.
13 | Older legacy URL pattern (pages ending in .html) was not covered by the redirect map. | 13 Jul | Fixed | 834 redirects imported and verified live 22 Jul (809 products, 25 categories, case-insensitive; renamed configurators map to their new pages).
14 | Sample test part numbers were embedded in the header lookup markup on every page. | 10 Jul | Fixed | Static samples removed; suggestion list populated only from real lookup results.
15 | Utility page page-template was published and visible to search engines. | 22 Jul | Fixed | Unpublished; the URL returns 404 and drops from the sitemap.

## Open Items
Item | Owner | Status | Note
Analytics: GA4 runs through Shopify's Google & YouTube channel. | Confirmed | Resolved | No separate GTM container expected on the storefront; tracking flows through the native Google channel integration.
Reviews app: Judge.me is installed; the original scope named Yotpo. | WT Farley | Decision | Confirm the app choice and where review widgets should appear.
8 configurator products built but held unpublished (IV poles, equipment stands, nebbulator, coiled oxygen hose). | WT Farley | Decision | Ready to publish once content and data are confirmed.
24 products have empty descriptions after legacy-notice cleanup; 2 active products have no image. | WT Farley | Content | List available on request.
30 SKUs are shared across multiple products (brand cross-listings, one near-duplicate product pair, one SKU on two products at different prices). | WT Farley | Decision | Needs a keep-or-merge call per case; affects lookup exactness.
Domain cutover (site currently on the myshopify.com preview address). | Launch task | Open | Scheduled as part of the launch plan.
Pre-launch checklist and launch plan. | Makro | Open | Drafted once QA sign-off lands.

## Test Coverage
Layer | Method | Coverage
Configurator engine | Automated crawl of every configurator product page: parse the engine data, validate structure (groups, choices, part codes, price add-ons, required flags), check the preview placeholder, pre-selection state, and add-to-cart wiring. | 31 live products, every option group and choice, re-run 22 Jul.
Configurator data | Programmatic comparison of store option data against the legacy site export: group sets, choice sets, part codes, price deltas (cents-exact), defaults, hidden flags, base prices. | 40 legacy configurable products, ~177 option groups.
Storefront | HTTP checks on key pages, menu link integrity, collection pages, product pages, images, search, redirects, cart add. Template error scanning on every fetched page. | Key pages, 91 collections, menu URLs, redirect samples.
Migrated data | Admin-side integrity audit: counts, duplicate SKUs, missing images, price anomalies, leftover test records. | 760 active products, 4,286 variants, 92 collections, customers, orders.
Interactive behavior | Manual browser passes on each feature as it was built and after each fix (Chrome on macOS), plus markup-level responsive verification at the theme's tablet and mobile breakpoints (990px / 600px). | Configurator flows, lookup flows, search, cart, navigation.

## Validation Matrix
Feature | Where | What to confirm | Desktop pass | Mobile pass | Tested by | Notes
Configurator: build a hose | /products/oxygen-hose | Pick a gas, options reveal, part number and price build up, layered preview updates, add to cart carries the selections.
Configurator: placeholder and image reveal | /products/15-foot-coiled-air-hose | Grey placeholder on load, nothing pre-selected, product photo appears on first pick, Reset returns to the placeholder.
Configurator: Color Coding | /products/oxygen-standard-body-click-regulator | Choosing a color swaps the preview image to that color.
Part-number lookup | Header search, Lookup toggle | A real part number lands on the right product with options prefilled. Typing a part number in regular search switches to Lookup automatically.
Search and filters | Header search, any collection | Quick search shows categories and products; filters stick while scrolling; infinite scroll loads more.
Cart and checkout entry | Any product | Sticky add-to-cart bar, mini cart contents, configurator selections listed on the line item.
Content pages | About, FAQ, Contact, Dealer, Testimonials | Copy, forms submit, dealer form fields match the old site's application.
Legacy links | Any old wtfarley.com product/category URL | Old links (including ..._p_NN.html / ..._c_NN.html) land on the matching new page via 301.
Mobile pass | Phone, any of the above | Configurator stacks with the preview on top; menus, filters and sticky bars usable.

## Performance
Measure | Result | Reading
Homepage HTML (compressed) | 74KB | Healthy. The page is markup-heavy but compresses well.
Product page HTML (compressed) | 49 to 54KB | Healthy, including the configurator engine data.
Product card images on desktop | 50 to 70% smaller after fix | Cards previously downloaded full-screen renditions; browsers now pick card-size ones (sample image: 52KB before, 14 to 24KB after). Applies to every card on collection pages, search and homepage sliders.
Third-party scripts | ~110KB platform baseline | Shopify checkout wallets and analytics loader (standard on every Shopify store), plus consent, reviews and email apps. Nothing anomalous.
Recommendation | Compress heavy homepage PNGs at source | A few homepage images are very large PNG source files (largest 1.14MB); modern browsers receive an optimized version automatically, but compressed exports would help older browsers.